## RESET SCHEDULE 2014
STORE RESET SCHEDULE FOR 2014 INITIAL DATE: 09/16/2013 REVISION NUMBER: 2 REVISION DATE: 3/31/2014
| NEW STORES | RENOVATION | LOZIER STORES | 2013 STORES
DATES | STORE | TYPE OF SET | OTHER INFO | SHELVING | LEAD
JAN. 5 - JAN. 7
JAN. 13 - JAN. 16
JAN. 19 - JAN - 21 | NO SET |  | MLK DAY
JAN. 26 - JAN. 28
FEB. 04 - FEB. 07 | NEW LONDON | DRY/CHILL/FRZ | SUPER BOWL | FULL SHELVING | Darnell/Diane
FEB. 09 - FEB. 11 | LAUGHLIN | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Diane/Darnell
FEB.16 - FEB. 18 | NO SET |  | PRESIDENT'S DAY
FEB. 23 - FEB. 25 | CHARLESTON AFB | DRY/CHILL/FRZ | SUN PULL DOWN | PARTIAL SHELVING | Darnell/Diane
MAR. 02 - MAR. 04 | PATRICK | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Diane
MAR. 05 - MAR. 06 | McCHORD | CLUB STORE | DAY SET | NO SHELVING | Darnell
MAR. 09 - MAR. 11 | FORT CAMPBELL | DRY/CHILL/FRZ | SUN PULL DOWN | PARTIAL SHELVING | Darnell
MAR. 16 - MAR. 18 | LOS ANGELES | DRY/CHILL/FRZ | SUN PULL DOWN | NO SHELVING | Diane
MAR. 22 - MAR. 24 | MITCHEL FIELD | DRY/CHILL/FRZ | SAT PULL DOWN | FULL SHELVING | Diane
MAR.30 - APR. 01 | OPEN
APR. 06 - APR. 08 | McCHORD | DRY/CHILL/FRZ | SUN PULL DOWN | PARTIAL SHELVING | Diane/Darnell
APR. 14 - APR. 17 | NO SET
APR. 20 - APR. 22 | NO SET |  | EASTER
APR. 27 - APR. 29 | QUANTICO | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Darnell/Diane
MAY. 04 - MAY. 06 | MCGUIRE | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Diane/Darnell
MAY. 11 - MAY. 12 | NO SET |  | MOTHER'S DAY
MAY. 13 - MAY. 15 | FORT BRAGG (NORTH) | DRY/CHILL/FRZ | TUES PULL DOWN | FULL SHELVING | Darnell/Diane
MAY. 18 - MAY. 20 | McCONNELL | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Diane
MAY. 21 - MAY. 23 | NO SET
MAY. 26 - MAY. 27 | NO SET |  | MEMORIAL DAY
JUN. 04 - JUN. 06 | GUNTER | DRY/CHILL/FRZ | NEW STORE | FULL SHELVING | Darnell
JUN. 16 - JUN. 18 | PITTSBURGH | DRY/CHILL/FRZ | NEW STORE | FULL SHELVING | Darnell/Diane
JUN. 15 | NO SET |  | FATHER'S DAY
JUN. 25 - JUN. 27 | ANNAPOLIS NSA | DRY/CHILL/FRZ | NEW STORE | FULL SHELVING | Darnell
JUN. 29 - JUL. 01 | FORT LEAVENWORTH | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Diane
JUL. 01 - JUL. 06 | NO SET |  | FORTH OF JULY
JUL. 13 - JUL.15 | KINGS BAY | DRY/CHILL/FRZ | SUN PULL DOWN | PARTIAL SHELVING | Darnell
JUL.20 - JUL. 22 | GRAND FORKS | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Diane
JUL. 28 - JUL. 30 | FORT POLK | DRY/CHILL/FRZ | NEW STORE | FULL SHELVING | Darnell
AUG. 02 - AUG. 04 | ARDEC(PICATINNY) | DRY/CHILL/FRZ | SAT PULL DOWN | FULL SHELVING | Diane
AUG.10 - AUG.12 | F.E. WARREN | DRY/CHILL/FRZ | SUN PULL DOWN | PARTIAL SHELVING | Diane
AUG.17 - AUG.19 | PEARL HARBOR | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Darnell
AUG. 21 - AUG. 23 | KANEOHE BAY | DRY/CHILL/FRZ | THURS PULL DOWN | FULL SHELVING | Darnell
AUG. 24 - AUG. 26 | MAYPORT | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Diane
AUG. 31 -SEPT. 02 | NO SET |  | LABOR DAY
SEPT. 07 - SEPT. 09 | FORT LEE | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Darnell/Diane
SEPT. 14 - SEPT. 16 | SMOKEY POINT | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Darnell
SEPT. 18 - SEPT. 20 | FORT LEWIS | DRY/CHILL/FRZ | THURS PULL DOWN | FULL SHELVING | Darnell
SEPT. 28 - 30 | COLUMBUS | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Diane
OCT. 05 - OCT. 07 | SAN DIEGO | DRY/CHILL | SUN PULL DOWN | FULL SHELVING | Darnell/Diane
OCT. 12 - OCT. 14 | NO SET |  | COLUMBUS DAY
OCT. 19 - OCT. 21 | FORT DRUM | DRY/CHILL/FRZ | SUN PULL DOWN | NO SHLEVING | Diane/Darnell
OCT. 26 - OCT. 28 | FORT HAMILTON | DRY/CHILL/FRZ | SUN PULL DOWN | FULL SHELVING | Darnell/Diane
`
Note on B10: Install date Jan. 6-7 Reset date 13-16
Note on B16: Club Store Day Set
Note on B22: No Installer needed Partial shelving needed upper shelving base shelving
Note on B34: Shelving Install June 2-3
Note on B35: Shelving install June 12-13
Note on B37: Shelving Install June 23-25
Note on B43: Shelving Install July 24-25